## Slide 1: Definition of Project and Project Cycle
A project is a unique venture to produce a set of outputs within clearly specified time, cost and quality constraints.
Projects differ from standard business operational activities as they:
• Are distinctive in nature, not involving a repetitive process.
• Have a define time-plan, with a specified start and end dates to meet the beneficiaries or funding agency’s requirements.
• Have an allocated budget, which should be spent to produce the deliverables.
• Have limited resources, such as labour, material and equipment.
• Involve a risk, as there is a level of uncertainty whether the objectives will be attained.

## Slide 2: The Project Cycle
Five stages are typically identified in the project cycle:
I Identification: generation of the initial project idea
II Definition and design: detailed design of the project addressing technical and operational aspects
III Proposal preparation, approval and financing: writing the project proposal, securing approval for implementation and arranging sources of finance
IV Implementation: implementation of project activities, with on-going checks on progress and feedback
V Evaluation: periodic review of project with feedback for next project cycle.
Exploring
Demand Creation
Participatory Decision Making, Analysis and Planning
Implementation
Ensuring Sustainability

## Slide 3
Definition of Project Proposal
A project proposal is a detailed description of a series of activities aimed at solving a certain problem.
The proposal should contain a detailed explanation of the:
• justification of the project;
• activities and implementation timeline;
• methodology; and
• human, material and financial resources required.

## Slide 4
Definition of Concept Note
A concept note is a summary of a proposal containing a brief description of the idea of the project and the objectives to be pursued.
Concept notes are prepare for:
some financing programs, funding agencies require a concept note before the submission of a full proposal.
donors without a formal call for proposals.

## Slide 5
Developing a Project Proposal and Concept Note
Getting Ready to Start a Project
Tips to start successfully your project writing:
Build a team for proposal development:
-Leader: coordinate all inputs and write core sections.
-Technical experts: brainstorming, give input in technical issues.
-Administrative staff: give accurate information related to budget.
Identify potential funding options
Review carefully the Community Action Plan or the Vision Statement of the Community.
Hold a kick-off meeting and share your ideas

## Slide 6: Project Planning: a part of the Project Design
The project design is one phase of the project cycle. It consists of two elements:
• project planning (formulation of project elements); and
• project proposal writing (converting the plan into a project document).
Project design is a result of both project planning and the project proposal. Both steps are essential to forming a solid project design.

## Slide 7: Project Planning: Developing a Project Idea
In order to identify the project idea, different aspects have to be considered:
Community vision of how the situation should be in a long term:
Desired situation
Current situation
gap
need
Project
Community needs assessment is a key step to project design, as it helps addressing the problems of the targeted local community.

## Slide 8
Setting priorities:
out of all the goals to be achieved, priorities have to be set to decide which project to carry out first. Priority problems falling into the scope of the stakeholders, your organisation, the State policy and the donor shall be selected.
Actor/Problem | Problem 1 | Problem 2 | Problem 3
Stakeholders | 3 | 1 | 2
State | 2 | 1 | 3
Donor | 3 | 2 | 1
Organisation | 2 | 3 | 1

## Slide 9: Humanitarian Program Cycle